## agile - sprint planni
Agile - Sprint Planning
Sprint 1 (Week 6)
Name | Subitems | Progress | Timeline - Start | Timeline - End | Developer | Dev status | Notes | Item ID (auto generated)
Clone GitHub repository |  | 100% | 2023-08-28 | 2023-08-28 | Jack Olivier, Nivethan Iyer, James La Fontaine, Harry Fisher, awijeratne@student.unimelb.edu.au | Done |  | 1813272648
Preliminary analysis of data |  | 100% | 2023-08-28 | 2023-09-02 | Jack Olivier, Nivethan Iyer | Done | Click blue speech bubble for details | 1813270054
Create generalised ETL script for the datasets |  | 100% | 2023-08-28 | 2023-09-03 | James La Fontaine | Done |  | 1813272011
Find ABS census data between Feb 2021 and August 2022 if possible |  | 100% | 2023-08-28 | 2023-09-02 | Harry Fisher, awijeratne@student.unimelb.edu.au | Done | Click blue speech bubble for details | 1813271818
Set up sprint planning on monday.com board |  | 100% | 2023-08-28 | 2023-09-03 | James La Fontaine | Done |  | 1813273960
|  | 100% | 2023-08-28 | 2023-09-03
Sprint 2 (Week 7)
Name | Subitems | Progress | Timeline - Start | Timeline - End | Developer | Dev status | Notes | Item ID (auto generated)
Conduct in-depth outlier analysis on the curated data |  | 100% | 2023-09-04 | 2023-09-10 | Nivethan Iyer | Done |  | 1813270058
Generate insights for the curated data | If you found NULL values after you joined the datasets, what did you do with them? How many were there? (fix during ETL), Was there any missing data that shouldn't be missing after joining to your external dataset? If anything was missing, how much was there and what did you do about it? (fix during ﻿ETL), If you decided to omit outliers, what does the distribution look like prior and after?, Geospatial Analysis, Any other interesting findings | 100% | 2023-09-04 | 2023-09-10 | Harry Fisher, James La Fontaine, Nivethan Iyer, Jack Olivier, awijeratne@student.unimelb.edu.au | Done |  | 1813272780
Subitems | Name | Progress | Timeline - Start | Timeline - End | Developer | Dev status | Notes | Item ID (auto generated)
| If you found NULL values after you joined the datasets, what did you do with them? How many were there? (fix during ETL) | 0% | 2023-09-04 | 2023-09-10 | James La Fontaine, Harry Fisher | Done |  | 1813988702
| Was there any missing data that shouldn't be missing after joining to your external dataset? If anything was missing, how much was there and what did you do about it? (fix during ﻿ETL) | 0% | 2023-09-04 | 2023-09-10 | James La Fontaine, Harry Fisher | Done |  | 1813988731
| If you decided to omit outliers, what does the distribution look like prior and after? | 0% | 2023-09-04 | 2023-09-10 | Nivethan Iyer | Done |  | 1813988747
| Geospatial Analysis | 0% | 2023-09-04 | 2023-09-10 | Jack Olivier | Done |  | 1813988758
| Any other interesting findings | 0% | 2023-09-04 | 2023-09-10 | Harry Fisher, awijeratne@student.unimelb.edu.au | Done |  | 1813988770
Created summarised notebook detailing relevant topics |  | 100% | 2023-09-04 | 2023-09-10 | James La Fontaine | Done | Click blue speech bubble for details | 1813273399
|  | 100% | 2023-09-04 | 2023-09-10
Sprint 3 (Week 8)
Name | Subitems | Progress | Timeline - Start | Timeline - End | Developer | Dev status | Notes | Item ID (auto generated)
ETL script is fully automated and runs end-to-end without issues |  | 100% | 2023-09-11 | 2023-09-17 |  | Done |  | 1813272167
Finalise previous week's work |  | 100% | 2023-09-11 | 2023-09-17 |  | Done |  | 1813274394
Curate a dataset that can be used for the Ranking System |  | 100% | 2023-09-11 | 2023-09-17 | James La Fontaine, awijeratne@student.unimelb.edu.au | Done | Click blue speech bubble for details | 1813274492
|  | 100% | 2023-09-11 | 2023-09-17
Sprint 4 (Week 9)
Name | Subitems | Progress | Timeline - Start | Timeline - End | Developer | Dev status | Notes | Item ID (auto generated)
Determine / create features and heuristics that rank merchants based on the curated data |  | 100% | 2023-09-18 | 2023-09-24 | James La Fontaine, awijeratne@student.unimelb.edu.au | Done | Click blue speech bubble for details | 1813271732
Build initial ranking system |  | 100% | 2023-09-18 | 2023-09-24 | Harry Fisher, Jack Olivier | Done |  | 1813276697
|  | 100% | 2023-09-18 | 2023-09-24
Sprint 5 (Mid-Semester Break)
Name | Subitems | Progress | Timeline - Start | Timeline - End | Developer | Dev status | Notes | Item ID (auto generated)
Initial ranking system should be in working order |  | 100% | 2023-09-25 | 2023-10-01 |  | Done |  | 1813273042
Segment merchants ourselves and identify top 10 merchants in each segment |  | 100% | 2023-09-25 | 2023-10-01 |  | Done | Click blue speech bubble for details | 1813275509
Determine the Top 100 merchants overall and the Top 10 merchants for the chosen segments |  | 100% | 2023-09-25 | 2023-10-01 |  | Done |  | 1813273067
Prepare a final summary notebook (include visualisations) |  | 100% | 2023-09-25 | 2023-10-01 |  | Done |  | 1813275791
|  | 100% | 2023-09-25 | 2023-10-01
Sprint 6 (Week 10)
Name | Subitems | Progress | Timeline - Start | Timeline - End | Developer | Dev status | Notes | Item ID (auto generated)
Walk tutor through findings and additional insights (3-5 mins max) |  | 100% | 2023-10-02 | 2023-10-02 | Harry Fisher | Done | Click blue speech bubble for details | 1813275871
Prepare draft for presentation |  | 100% | 2023-10-02 | 2023-10-04 | Nivethan Iyer, Harry Fisher | Done |  | 1813276047
Finalise slides for presentation |  | 100% | 2023-10-02 | 2023-10-06 | James La Fontaine, Harry Fisher, Jack Olivier, awijeratne@student.unimelb.edu.au, Nivethan Iyer | Done |  | 1813276371
|  | 100% | 2023-10-02 | 2023-10-06
Sprint 7 (Week 11)
Name | Subitems | Progress | Timeline - Start | Timeline - End | Developer | Dev status | Notes | Item ID (auto generated)
Tidy and collate code and repository for submission |  | 100% | 2023-10-09 | 2023-10-15 |  | Done |  | 1813273085
Perform presentation |  | 100% | 2023-10-09 | 2023-10-20 |  | Done |  | 1813276270
|  | 100% | 2023-10-09 | 2023-10-20

## agile - sprint planni-updates
Agile - Sprint Planning | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
1813270054 | Preliminary analysis of data | Update |  | James La Fontaine | 30/August/2023 06:38:28 PM | Visualisations of feature distributions, NULL and basic outlier analysis, get familiar with the data and try to work out what kind of preprocessing needs to be performed in the ETL script. | 0 |  | 1922025
1813271732 | Determine / create features and heuristics that rank merchants based on the curated data | Update |  | James La Fontaine | 30/August/2023 06:18:29 PM | >* Example: predict consumer growth rate w.r.t merchants + avg spend amount * An initial test set may be released which can be used to see how well your ranking system performs. * Groups can train a model to predict a certain feature that will be used in rankings, such as forecasting merchant revenue or the number of customers over time based on historical data. | 0 |  | 1921744
1813271818 | Find ABS census data between Feb 2021 and August 2022 if possible | Update |  | James La Fontaine | 30/August/2023 06:37:38 PM | Recommended to look at the ABS census data that contain Statistical Area fields (i.e SA2). | 0 |  | 1922007
1813273399 | Created summarised notebook detailing relevant topics | Update |  | James La Fontaine | 30/August/2023 06:06:44 PM | >* If you found NULL values after you joined the datasets, what did you do with them? How many were there? * Was there any missing data that shouldn't be missing after joining to your external dataset? If anything was missing, how much was there and what did you do about it? * If you decided to omit outliers, what does the distribution look like prior and after? * Any other interesting findings. * Include geospatial visualisations where possible. | 0 |  | 1921519
1813274492 | Curate a dataset that can be used for the Ranking System | Update |  | James La Fontaine | 30/August/2023 06:16:18 PM | >* A delta file of transactions to be treated as fraud is available. It is up to your group to remove these transactions or add a new field denoting fraud i.e an 𝚒𝚜_𝚏𝚛𝚊𝚞𝚍 boolean field. * Groups may see the distribution of the delta file containing fraud transactions and create simple models to predict whether a transaction may be fraud in future (i.e high volume transactions for a consumer who rarely purchases). | 0 |  | 1921716
1813275509 | Segment merchants ourselves and identify top 10 merchants in each segment | Update |  | James La Fontaine | 30/August/2023 06:20:48 PM | >* Groups should identify at least three and at most five different segments to classify merchants. For example, clothing vs technology vs groceries. * Once the segments have been decided upon, students should curate their ranking systems for each segment. | 0 |  | 1921777
1813275871 | Walk tutor through findings and additional insights (3-5 mins max) | Update |  | James La Fontaine | 30/August/2023 06:24:16 PM | This week's checkpoint marks will be allocated based on the quality of insights and justification over the final ranking system. | 0 |  | 1921831